**Project UKRAINE-ROMANIA-MOLDOVA (CEF)**

This project addresses road safety measures in the proximity of Galati (Romania), the widening of the road connecting the Galati and Reni Border Crossing Points (BCP), design and construction of the northern bypass to Giurgiulesti, the construction of access roads to the BCP area in Galati /Giurgiulesti/Reni, as well as construction of two HGV parkings

located in Giurgiulesti (Moldova) and in proximity of the Reni BCP (Ukraine). The project is located between Ukraine (UA), Moldova (MD), and Romania (RO) on the TEN-T Comprehensive network. This route plays a key role in the EU Solidarity Lanes to facilitate Ukraine’s agricultural export and bilateral trade with the EU, in particular in the context

of the Russian war of aggression. By creating a continuous and efficient customs corridor, the project will reduce the border process time in all concerned BCPs and will improve the accessibility and future development of the port area of Giurgiulesti.

Duration

09/2024 – 02/2028

Total budget: 26 131 928

EU funding: 13 065 964.01

Curent status as of now:

1. **Development of Parking and Service Areas near the Reni – Giurgiulești – Galați Border Crossing (Restoration Service in Odesa Region)**
	* The procurement procedure for project documentation development has been completed.
	* Project documentation is ready and has been submitted for approval to the Recovery Agency.
	* Procurement for construction works is planned for May 2025.
2. **Project Management (Recovery Agency)**
	* The procurement procedure for the work package is expected by mid-April.
	* The technical assignment has been developed and is currently being adjusted by the relevant departments.

Contracts are planned to be signed by mid-May 2025.